## Weekly capacity
Plan the work by role
Synthetic planning assumptions. Not history or a forecast.
Amber cells are editable. Hours are per week unless stated.
| Preparation | Review
Work hours needed | 72 | 18
Work hours available | 60 | 24
Uncovered hours | 12 | 0
Unused hours | 0 | 6
Planning result | Extra hours needed | Hours cover this plan
Review time cannot replace preparation time without qualified cover.
Planning inputs
Requests planned this week | 36
| Preparation | Review
Hours per request | 2 | 0.5
People in this role | 2 | 1
Scheduled hours per person | 40 | 40
Other commitments, role total | 12 | 8
Absence hours, role total | 8 | 8
Inputs usable? | TRUE | TRUE
Calculation details
Available = people × hours − commitments − absence | 60 | 24
Needed = requests × hours per request | 72 | 18
Uncovered = max(needed − available, 0) | 12 | 0
Unused = max(available − needed, 0) | 0 | 6
All numbers are invented for this example. Change the amber cells.
Other commitments include meetings, admin and other assigned work.
Enter commitments during attended time. Do not subtract absence twice.
No automatic role substitution, overtime or productivity gain is assumed.
Weekly hours do not prove a daily schedule or timely completion.
Requests use average assumed effort. Check variation and urgent work.
12 uncovered hours means hours to address, not an automatic new hire.
Check qualifications, onboarding time, budget and dates before adding help.
Missing, negative, fractional people/requests or impossible hours block results.
Method context: deltek.com/resources/articles/capacity-planning/